## Introduction
| Title |  | Earned Value Analysis
Navigation | Content |  | With this file, you can easily compare your project Planed Value [PV] vs Earned Value [EV] vs Actual Cost [AC]
View projects metrics for selected milestone date [View Period End Date]
Setup |  |  | Forecast Estimated Cost at Completion [EAC] and Estimated Date of Completion based on milestone date [View Period End Date]
Planned |  |  | Easily print the "Summary" sheet landscape mode.
Actuals
Summary
| Customization difficulty (1-3) |  | 1
| Explanation of sheets | Setup: | The most important sheet in this Template. You must fill in Project Start Date and Project Start Date.
Period Length can be (Days, Weeks, Months, Quarters or Years). Planning Unit can be Hours or Money (Cost).
|  | Planned: | In this sheet you should fill in all planned cost.
Based on Planning Unit selection in "Setup" sheet values entered for each period should be shown in Hours or Money. If Planned Value is Hours it is important to define hourly cost for each task in column "C".
|  | Actuals: | In this sheet you should fill in all actual cost
Actual Percentage of Task Fulfilment (first table in this sheet) is placeholder for percentage of task is completed in each period. All percentages for each task are summed in column "C". Please note that total percentage cannot be more then 100%
Actual Task Cost (second table in this sheet) will reflect costs from "Planned Sheet". You can change any value here with planned values. All changed values will automatically get yellow background color.
|  | Summary: | Final sheet where all end results are shown. You can change View Period End Date from dropdown menu (cell "E7") to see metrics at any period of the project.
| How to customize | 1) | You can change names in top section of "Setup" sheet (Company Name, Project Name, Created By) to fit your proposes. These names will be automatically transformed to "Summary" sheet.
|  | 2) | You can change names of the tasks in "Planned" sheet. These names will be automatically transformed to all other sheets in this template.
|  | 3) | If needed, check out the video in which I walk you through each and every step!
| Definitions for key term |  | Planed Value [PV] - is the approved value of the work to be completed in a given time. It is the value that you should have been earned as per the schedule.
Earned Value [EV] - is the value of the work actually completed to date. If the project is terminated today, Earned Value will show you the value that the project has produced.
Actual Cost [AC] - is the total cost incurred for the actual work completed to date. Simply put, it is the amount of money you have spent to date.
Cost Variance [CV] - indicates how much over or under budget the project is. (Positive = indicates how much under budget the project ¦Negative = indicates how much over budget the project)
Schedule Variance [SV] - Schedule Variance (SV) indicates how much ahead or behind schedule the project is. (Positive = Indicates we are ahead of schedule ¦ Negative = Indicates we are behind of schedule
Cost Performance Index [CPI] - is a measure of the financial effectiveness and efficiency of a project. It represents the amount of completed work for every unit of cost spent.
Schedule Performance Index [SPI] - is a measure of how close the project is to being completed compared to the schedule.
Estimated Cost at Completion [EAC] - is the forecasted cost of the project when a project has already been started.
Estimated Date of Completion - is project completion date as per current parameters.

## Setup
Company Name
Project Name
Created By
Project Start Date |  | Please provide project Start Date.
Project End Date
Period Length | Weeks
Planning Unit | Cost (Money)

## Planned
Planned Cost | [21 empty] | TOTAL COST
Task | Cost per Hour
Task 01 | [21 empty] | 0
Task 02 | [21 empty] | 0
Task 03 | [21 empty] | 0
Task 04 | [21 empty] | 0
Task 05 | [21 empty] | 0
Task 06 | [21 empty] | 0
Task 07 | [21 empty] | 0
Task 08 | [21 empty] | 0
Task 09 | [21 empty] | 0
Task 10 | [21 empty] | 0
Task 11 | [21 empty] | 0
Task 12 | [21 empty] | 0
Task 13 | [21 empty] | 0
Task 14 | [21 empty] | 0
Task 15 | [21 empty] | 0
Task 16 | [21 empty] | 0
Task 17 | [21 empty] | 0
Task 18 | [21 empty] | 0
Task 19 | [21 empty] | 0
Task 20 | [21 empty] | 0
0
Planed Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Actuals
Actual Percentage of Task Fulfilment
Task | Task Fulfilment (%)
Task 01 | 0%
Task 02 | 0%
Task 03 | 0%
Task 04 | 0%
Task 05 | 0%
Task 06 | 0%
Task 07 | 0%
Task 08 | 0%
Task 09 | 0%
Task 10 | 0%
Task 11 | 0%
Task 12 | 0%
Task 13 | 0%
Task 14 | 0%
Task 15 | 0%
Task 16 | 0%
Task 17 | 0%
Task 18 | 0%
Task 19 | 0%
Task 20 | 0%
0%
Actual Task Cost | [21 empty] | TOTAL COST
Task | Actual Cost per Hour
Task 01 | 0 | [20 empty] | 0
Task 02 | 0 | [20 empty] | 0
Task 03 | 0 | [20 empty] | 0
Task 04 | 0 | [20 empty] | 0
Task 05 | 0 | [20 empty] | 0
Task 06 | 0 | [20 empty] | 0
Task 07 | 0 | [20 empty] | 0
Task 08 | 0 | [20 empty] | 0
Task 09 | 0 | [20 empty] | 0
Task 10 | 0 | [20 empty] | 0
Task 11 | 0 | [20 empty] | 0
Task 12 | 0 | [20 empty] | 0
Task 13 | 0 | [20 empty] | 0
Task 14 | 0 | [20 empty] | 0
Task 15 | 0 | [20 empty] | 0
Task 16 | 0 | [20 empty] | 0
Task 17 | 0 | [20 empty] | 0
Task 18 | 0 | [20 empty] | 0
Task 19 | 0 | [20 empty] | 0
Task 20 | 0 | [20 empty] | 0
| 0 | [20 empty] | 0
Actual Cost |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Calculations (hidden)
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| Planed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Performed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget Cost of Work Scheduled [BCWS] | Planed Value [PV] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Budget Cost of Work Performed [BCWP] | Earned Value [EV] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Cost of Work Performed [ACWP] | Actual Cost [AC] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Performance Index [CPI]
Schedule Performance Index [SPI]
View Period End Date
View Period End Date Index
Budget Cost of Work Scheduled [BCWS] | Planed Value [PV]
Budget Cost of Work Performed [BCWP] | Earned Value [EV]
Actual Cost of Work Performed [ACWP] | Actual Cost [AC]

## Summary
Company Name
Project Name
Created By
View Period End Date
Project Start Date
Project End Date
Planed Value [PV]
Earned Value [EV]
Actual Cost [AC]
Cost Variance [CV]
Schedule Variance [SV]
Cost Performance Index [CPI]
Schedule Performance Index [SPI]
Estimated Cost at Completion [EAC]
Estimated Date of Completion

## Dropdown (hidden)
Period |  | Plus | Planning Unit
Days |  | 1 | Hours
Weeks | #VALUE! | 7 | Cost (Money)
Months | #VALUE!
Quarters | #VALUE! | #VALUE!
Years | #VALUE!